Minutes of the Meeting P321

Vera Navis Ship Design (VNSD) – CorPower Ocean (CPO)

Date & Time: 28/10/26 09:30

Location: WEB

Name; ORG.; Email. Filipe Belga (Organizer); VNSD; filipe.belga@veranavis.com. Lidia Correia; VNSD; lidia.correia@veranavis.com. Cobus Botes; CPO; cobus.botes@corpowerocean.com. Joel Ruesen; CPO; joel.ruesen@corpowerocean.com. Simon Borjeson; CPO; simon.borjeson@corpowerocean.com. Luis.

Redactor: Filipe Belga (VNSD)

- Contents

Contents	2

1.	Purpose of the Meeting	2

2.	Meeting Agenda	2

3.	Meeting Summary	3

4.	Actions List	5

# Purpose of the Meeting

Weekly Technical Meeting

# Meeting Agenda

Invoicing discussion

General updates and actions list

Discussion on DNV’s proposed framework

# Meeting Summary

The meeting started with a review of the actions list. Following the extraordinary meeting held in October 22, recorded in Minutes of the Extraordinary Meeting 22-10-2026, the actions associated to the WEC Bay WP have been updated.

WEC Installer — proposed rules & regulatory mapping

Gents,

Please find suggestion to first draft of requirement framework.

Choice of flag/maritime administration may result in minor adjustments to the below-listed items. Still the main approach indicated by class string and requirements drafted should work as a convincing assurance case to present to maritime administrations in order to get flag assigned.

Please consider these items as a first draft subject for your consideration and conclusion.

Main assumptions

- Hybrid operations - battery to contribute with propulsion (Battery(power))

- Remote operations for navigating vessel in transit plus installation/retrieval of WEC

- Auto-remote concept based on: Operations on board including station keeping ability combined with lifting operations, mode of operations defined as Remote Control, location of control identified concluded to be Hybrid Control

- Station keeping ability while WEC-handling is performed

- This concept fits into a maritime flag regime, using SOLAS for cargo ships as a basis

-----------------------.



| Main items | DNV Rules and standard | Note | - |
| --- | --- | --- | --- |
| Class notation | ✠ 1A WEC Installer Vessel Battery(Power) E0 DPS(1) AROS-OPS(RC,HC) |  |  |
| Digital integrity - Cyber Secure | DNV-RU-SHIP Pt.6 Ch.5 Sec.21 | Framework for design and implementation of barriers to identify, protect, detect, respond, and recover from cyber security incidents. |  |
| Station keeping – DPS(1) | DNV-RU-SHIP Pt.6 Ch.3 Sec.1 | Dynamic positioning system with an independent joystick system back-up and a position reference back-up. |  |
| Unattended machinery spaces – E0 | DNV-RU-SHIP Pt.6 Ch.2 Sec.2 | Safety for vessels operating with periodically unattended machinery spaces |  |
| Electrical energy storage – Battery(Power) | DNV-RU-SHIP Pt.6 Ch.2 Sec 1 | Requirement for safety and availability of electrical energy storage (EES) installations on board vessels. |  |
| Autonomy and remote operation - AROS-OPS(RC,HC) | DNV-RU-SHIP Pt.6 Ch.12 DNV-CG-0264 | Define systematics, functional, and procedural requirements for the autoremote vessel, the systems used on board and off-ship, the remote operation centre (ROC), and the connectivity needed for autoremote vessel operations |  |
| Lifting appliances and deck equipment | DNV-ST-0378 | Offshore and platform lifting appliances with requirements for integrity of winches, hoist arrangement, etc intended for load handling outside vessel while at sea |  |
| Safety and arrangement | DNV-RU-SHIP Pt.4 Ch.11 | Fire safety |  |
| Launch and recovery system of ROV | DNV-ST-0378, Sec 13 | Safety and performance of launch and recovery arrangement for ROV |  |

Please revert with your immediate reflections on the above and any update on maritime administration.

Comments to DNV proposed framework:

- DP: Downgrade to DP 0 but keep DP1 requirement in practice: Dynamic positioning system with an independent joystick system back-up and a position reference back-up.

basically class the basic DP system but not class the level of redundancy

- E0 enquire why that is?

- Cyber Secure: DNV is presenting as a rule but not as part of the string. This means we have margin to discuss this. Consider downgrading as much as possible the requirements for cyber security to reduce costs while ensuring the technical specifications are sufficiently clear so that OEMs understand they should provide cyber-secure equipment.

- Final List of drawings

- Catamaran strength requirements still missing

- Actions:

VNSD to study requirements on DP, E0 and cyber security

Prepare framework document with what we intend to discuss on the 30th

Joel will bridge with RC-Docks

Send agenda to DNV Monday 2nd, pending RC-Docks

Meet with DNV on the 5th, pending RC-Docks

Action: engage MT to ask for cost of a full compliance DP system for this particular notation

Action: Kick-off OEM engagement (DP, thrusters, electrical)

Action: Proceed with shipyard engagement (inc. technical documentation) independent of the AiP process

Action: Share preliminary issues of Construction Plan, Report winch, Report beam seas, Report quartering seas + update MRD

# Actions List

Table 1 - Actions List

| Subject | Action | Responsible | Deadline | Status |
| --- | --- | --- | --- | --- |
| Regulatory | CPO to contact DNV regarding the delay in issuing the class notation and list of drawings for AiP | Joel Ruesen | 16-10-2026 | Closed |
| Regulatory | Engage with flag to assess regulatory implications of the project (after HAZID actions have settled) | Filipe Belga | Pending DNV | Opened |
| Regulatory | Review and issue annexes A (technical documentation) and B (schedule) on PEP | Filipe Belga | Pending DNV | Opened |
| Regulatory | Definition of the AiP documentation | Filipe Belga | Pending DNV | Opened |
| Regulatory | VNSD to issue equipment number calculation report | Filipe Belga | Pending DNV | Opened |
| CONOPS | CPO to process Niels feedback to the CONOPS from an operational perspective | Joel Ruesen | 16-10-2026 | Opened |
| CONOPS | CPO to share the revised CONOPS, incorporating RC-Dock’s input. | Joel Ruesen | 16-10-2026 | Opened |
| CONOPS | Arrange a joint session with MT and RC-Dock to translate the CONOPS into design requirements and align the Build Specifications, pending DNV feedback | Joel Ruesen | 23-10-2026 | Opened |
| WEC Bay WP | CPO to arrange a session to review WEC Bay gate concept development and establish the requirements for VNSD’s involvement | Joel Ruesen | 23-10-2026 | Closed |
| WEC Bay WP | VNSD to submit a VO once the scope of the WEC Bay gate transfer to WP1 is clarified | Lidia Correia | 26-10-2026 | Opened |
| WEC Bay WP | Relative height analysis | Cobus Botes | 26-10-2026 | Opened |
| WEC Bay WP | Input on hinge locations | Cobus Botes | 26-10-2026 | Opened |
| WEC Bay WP | Impact/design pressures for selection of fendering material | Cobus Botes | 06-11-2026 | Opened |
| DP | Arrange a session with MT to address contractual DP performance requirements and support the DP assessment calculations, pending DNV feedback | Luis Batista | Pending DNV | Opened |
| DP | DP assessment | Filipe Belga | Pending DNV | Opened |
| Directional stability | VNSD to present the directional stability assessment strategy, pending DNV feedback | Filipe Belga | 23-10-2026 | Opened |
| Directional stability | VNSD to develop directional stability calculations, pending DNV feedback | Filipe Belga | 06-11-2026 | Opened |
| Structures | CPO (Cobus) to clarify the outstanding mission-equipment design loads, footprints and 3D models | Cobus Botes | 16-10-2026 | Closed |
| Structures | Contact DNV to clarify the assumptions for the mission-equipment foundation structural analyses | Filipe Belga | Pending CPO | Opened |
| Structures | VNSD to engage in FEA to include the mission equipment load path | Filipe Belga | 16/10/2026 | Opened |
| Structures | VNSD to engage in FEA to study beam seas and quartering seas phenomena affecting the cross deck | Filipe Belga | 16/10/2026 | Opened |
| Hull shape | VNSD to refine hull shape (transom, bow, filleted corners) | Filipe Belga | Pending DNV and FEA | Opened |
| Stability | VNSD to review the vessel layout for the impact of relocating tank air pipes further inboard | Filipe Belga | 14-10-2026 | Opened |
| Stability | CPO to provide a diagram showing the concept for the pull-down winch as justification for force application on main deck | Cobus Botes | 01-10-2026 | Opened |
| Renders | VNSD to issue final rendered views and aesthetics | Filipe Belga | Pending CPO | Opened |
| Weight | Remove deadweight from weight control list | Filipe Belga | Pending DNV | Opened |
| Weight | VNSD to update the LSW estimate before freezing the design, managing CPO’s/VNSD’s uncertainties (mission equipment) as design margins | Filipe Belga | Pending DNV | Opened |
| Electrical | VNSD will develop a one Line diagram schematics | Filipe Belga | Pending DNV | Opened |
| Electrical | VNSD will carry out an electrical load balance | Filipe Belga | Pending DNV | Opened |